## ProjectSchedule
RiskTrace — Project Schedule
Supply chain risk analysis for open-source software dependencies |  | Project Start: | 2026-08-03
Abhishek Batra Roll No: 1024030463 Shaurya Sangwan Roll No: 1024030462 Sushain Sharma Roll No: 1024030439 |  | Status Date: | 2026-09-13
[6 empty] | 2026-08-03 | [6 empty] | 2026-08-10 | [6 empty] | 2026-08-17 | [6 empty] | 2026-08-24 | [6 empty] | 2026-08-31 | [6 empty] | 2026-09-07 | [6 empty] | 2026-09-14 | [6 empty] | 2026-09-21
 | time axis 2026-08-03 to 2026-09-27
TASK | ASSIGNED TO | PROGRESS | START DATE | END DATE | DAYS | time axis 2026-08-03 to 2026-09-27
PHASE 1 — GROUP FORMATION AND PROJECT IDEATION |  | 100% | 2026-08-03 | 2026-08-09 | 7
Brainstorm project ideas and identify possible problem areas | Abhishek Batra, Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-03 | 2026-08-09 | 7
Finalize the RiskTrace project concept and project scope | Abhishek Batra, Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-03 | 2026-08-09 | 7
Prepare and practice the project pitch | Abhishek Batra, Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-03 | 2026-08-09 | 7
PHASE 2 — ELEVATOR PITCH |  | 100% | 2026-08-10 | 2026-08-16 | 7
Design and create the elevator pitch presentation | Shaurya Sangwan | 100% | 2026-08-10 | 2026-08-16 | 7
Prepare pitch content and presentation material | Abhishek Batra, Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-10 | 2026-08-16 | 7
Present the RiskTrace elevator pitch in class | Abhishek Batra, Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-10 | 2026-08-16 | 7
PHASE 3 — DATASET, PROPOSAL AND REPOSITORY SETUP |  | 100% | 2026-08-17 | 2026-08-23 | 7
Research and find a suitable vulnerability dataset | Shaurya Sangwan | 100% | 2026-08-17 | 2026-08-23 | 7
Curate and organize the vulnerability dataset | Shaurya Sangwan | 100% | 2026-08-17 | 2026-08-23 | 7
Research background information and related work | Abhishek Batra, Sushain Sharma | 100% | 2026-08-17 | 2026-08-23 | 7
Gather raw content for the project proposal | Abhishek Batra, Sushain Sharma | 100% | 2026-08-17 | 2026-08-23 | 7
Structure and organize the project proposal | Shaurya Sangwan | 100% | 2026-08-17 | 2026-08-23 | 7
Set up the GitHub repository and initial project structure | Shaurya Sangwan | 100% | 2026-08-17 | 2026-08-23 | 7
PHASE 4 — PROPOSAL REVISIONS AND SYSTEM ARCHITECTURE |  | 100% | 2026-08-24 | 2026-08-30 | 7
Incorporate teacher feedback into the project proposal | Shaurya Sangwan, Sushain Sharma | 100% | 2026-08-24 | 2026-08-30 | 7
Convert and prepare the proposal in LaTeX | Sushain Sharma | 100% | 2026-08-24 | 2026-08-30 | 7
Finalize overall system architecture | Abhishek Batra, Shaurya Sangwan | 100% | 2026-08-24 | 2026-08-30 | 7
Design backend service architecture and data flow | Abhishek Batra, Shaurya Sangwan | 100% | 2026-08-24 | 2026-08-30 | 7
Define frontend structure and technology stack | Abhishek Batra, Shaurya Sangwan | 100% | 2026-08-24 | 2026-08-30 | 7
PHASE 5 — UML, SYSTEM DESIGN AND INITIAL IMPLEMENTATION |  | 100% | 2026-08-31 | 2026-09-06 | 7
Create Use Case Diagram | Shaurya Sangwan | 100% | 2026-08-31 | 2026-09-06 | 7
Create Level 0 Data Flow Diagram | Sushain Sharma | 100% | 2026-08-31 | 2026-09-06 | 7
Create Level 1 Data Flow Diagram | Sushain Sharma | 100% | 2026-08-31 | 2026-09-06 | 7
Create Level 2 Data Flow Diagram | Abhishek Batra | 100% | 2026-08-31 | 2026-09-06 | 7
Start code implementation | Abhishek Batra, Shaurya Sangwan | 100% | 2026-08-31 | 2026-09-06 | 7
Initialize GitHub Pages | Abhishek Batra | 100% | 2026-08-31 | 2026-09-06 | 7
PHASE 6 — IMPLEMENTATION AND DOCUMENTATION |  | 100% | 2026-09-07 | 2026-09-13 | 7
Create Activity Diagram | Shaurya Sangwan | 100% | 2026-09-07 | 2026-09-13 | 7
Create ER Diagram | Abhishek Batra | 100% | 2026-09-07 | 2026-09-13 | 7
Create prototype presentation (PPT) | Shaurya Sangwan | 100% | 2026-09-07 | 2026-09-13 | 7
Prepare project report | Abhishek Batra | 100% | 2026-09-07 | 2026-09-13 | 7
Restructure repository structure | Abhishek Batra, Shaurya Sangwan | 100% | 2026-09-07 | 2026-09-13 | 7
Update GitHub Pages | Shaurya Sangwan | 100% | 2026-09-07 | 2026-09-13 | 7
Build initial full-stack MVP | Abhishek Batra | 100% | 2026-09-07 | 2026-09-13 | 7
Implement the project Gantt chart and milestone tracking | Shaurya Sangwan | 100% | 2026-09-07 | 2026-09-13 | 7
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
RiskTrace
University Software Engineering Project
Project Overview
RiskTrace is a supply chain risk analysis tool for open-source software dependencies. It analyzes dependencies, performs vulnerability matching, calculates risk scores, and provides results through a frontend dashboard.
Team Members
Abhishek Batra — 1024030463 Shaurya Sangwan — 1024030462 Sushain Sharma — 1024030439
Project Start: August 3, 2026